## Duration
Tasks | planned duration (weeks) | actual duration (weeks) | cumulative planned durations | cumulative actual durations | corrective
start product transformation using the ball mill | 6 | 3 | 6 | 3 | 3
look for a waste management system | 2 |  | 8 | #N/A | 8 | Current Progress | 3
[6 empty] | Max Planned | 8
[6 empty] | Days Left | 1
[6 empty] | Requires rates | 5

## Cost
Tasks | planned cost | actual cost | cumulative planned cost | cumulative actual cost | corrective
start product transformation using the ball mill | 2200000 | 3000000 | 2200000 | 3000000 | 3000000
look for a waste management system | 5000000 |  | 7200000 | #N/A | 7200000 | Current Progress | 3000000
[6 empty] | Max Planned | 7200000
[6 empty] | Days Left | 1
[6 empty] | Requires rates | 4200000